## SY22 MIS
Engagement Domain | Strategy Description to Address Engagement Need

## Implementation Plan
Engagement Strategy | Cooperative Learning (Cooperative Learning is the framework we selected as a staff to ensure all students have a voice and engage in sustained inquiry and reflection.)
Engagement Need Alignment | All students report and demonstrate meaningful behavioral, emotional, and cognitive engagement. This work will benefit all students and teachers in all grades.
Root Causes Alignment | Based on our assessment results we could be more intentional about fully engaging all students. Evidence suggests that some students are engaged more than others (cognitively, emotionally, and behaviorally) in meaningful learning. By setting this as a goal, we will increase our capacity to effectively engage ALL students. We also want to develop capacity and accountability for students and teachers to reach optimum engagement in lifelong learning.
Implementation Goals | 1. All students report engaging cognitively, emotionally, and behaviorally in meaningful learning via daily, multimodal opportunities to sustain and share their learning and thinking as measured by a student engagement assessment. 85% of students will demonstrate engagement in a cooperative learning structure during classroom observations. 90% of students will participate in restorative circles, conversations, and mediations to maintain emotional engagement (added 11/21) 2. 85% of teachers report high levels of engagement in professional learning This is measured through feedback on the PD surveys. 100% of teachers demonstrate cooperative learning, and restorative practices as measured through classroom observations. (revised 11/21)
Baseline Data Points Spring 2021 | CCS teachers and staff reported varying levels of engagement when considering the skills they have to support diverse learners. Almost 2/5 of teachers and staff reported they do not have the skills and support to effectively engage English language learners, students who have an IEP/504, and students who are identified as gifted and talented. Staff reported that 58% of students are frequently engaged and 42% are nearly always engaged. Staff reported that diverse learners are slightly less engaged overall, and less consistently engaged than gifted students. Staff reported 27% of ELLs are occasionally engaged, 64% are frequently engaged, and 9% are nearly always engaged. Staff reported that 17% of 504/IEP are occassionally engaged, 83% are frequently engaged, and 0% are nearly always engaged. Staff reported that 67% of gifted students are frequently engaged and 33% are nearly always engaged. Overall CCS students reported high levels of engagement. More students reported less frequently sharing their thinking and learning, frequently not finding it hard to stop working on classroom activities, and are infrequently challenged in relation to other questions asked in the student survey. In our classroom observations (Kaci, Diana, Sam, Angie), we saw teachers engaging students using multiple modalities and structures. Overall, student participation was high. Following observations, we noted various degrees of students doing the cognitive lift in the classroom (explaining, making connections, addressing questions) and we weren't always sure if students who were quiet, were engaged emotionally or cognitively. *** Update 11/2021; We have noticed an uptick in social-emotional needs and interpersonal conflict as we have returned to in-person learning full time. As a result, we feel that we need to both proactively foster student emotional and behavioral engagement and prevent and respond to interpersonal conflicts that may inhibit effective cooperation learning.
Interim Target #1 Fall 2021 | By January 1, 2022 all students participate in cooperative learning structures and restorative practices to sustain and share their learning and thinking at least twice a week with each teacher. All students reflect on their engagement once a week. All teachers participate in professional learning and implement cooperative learning structures and restorative practices to ensure students are accountable for their behavioral, emotional, and cognitive engagement. (revised 11/21)
Milestone 1 | Cooperative Learning Leadership Training - Summer 2021
By August 1st, teacher leaders attend Kagan Leader Training and become our resident Kagan experts.
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Sign Up for Kagan Leader Training | Sam | Angie and Diana | Angie and Diana attend the three day workshop | 2021-07-12 | 2021-07-14 | https://www.kaganonline.com/workshops/events/index.php | YES | Excellent training - consider bringing a Kagan trainer to CCS.
Select Kagan Strategies for Professional development | Angie and Diana | Teachers/Students | Angie and Diana will select high impact kagan strategies by our meeting on 7/16/21 | 2021-07-12 | 2021-07-16
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 2 | Cooperative Learning Schoolwide Implementation - Fall 2021
By December 15th, all teachers will be implementing cooperative learning strategies twice a week and will have participated in three cycles of professional growth to ensure students are accountable for their behavioral, emotional, and cognitive engagement. (Cycle: learn; pick a structure to implement; invite a coach to observe implementation; receive feedback from coach; reflect in writing and discussion on implementation of structure) |  |  |  | 2021-10-04
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Add 5-8 teacher to lead team and decide frequency of leadership meetings | Sam, Angie, Diana | All Teachers | Team expands; teachers meet regularly. | 2021-07-01 | 2021-09-01 | meetings on shared calendar | x
Book a 1 day Kagan PD workshop - on site | Sam | All teachers | Kagan booked and completed | 2021-07-16 | 2021-09-17 |  | x
1st Semester Schedule and syllabus for Cooperative Classrooms Professional Development Series (Alternating Structured PD with discussion/reflection/plan time)Intro to cooperative learning; the why of engagement w/ reflection; scaffolding cooperative learning PD #2; PD on inside/outside structure for portfolio reflections; lesson planning, blooms taxonomy; teaching kids about engagement skills and strategies, learning intentions, ) ***1st and all PD with cooperative structures embedded | Leadership Team | All Teachers | All teachers attend cooperative learning professional development 1 hour/week and report high levels of engagement as measured via PD engagement feedback | 2021-07-15 | 2021-08-16 | PD Schedule and Stipend Structure
Purchase materials and supplies for professional development - create a resource table for staff to access resources | Sam | All Teachers | Materials are bought to support PD starting 8/16 - Cooperative Learning Book by kagan | 2021-07-25 | 9/17/21;
All teachers attend staff meetings and fully participate in professional development sessions. We develop a team approach to implementing cooperative learning structures - for example, PE teacher comes to leadership/coaching team for ideas on how to implement structures in PE. | Sam | All teachers | Attendance tracker; structure log sheet (kagan) | 2021-10-04 | 2021-12-13
Develop and administer an engagement and professional development feedback form for teachers. | Leadership Team | All Teachers | CCS Cooperative Classrooms PD Feedback Form: | 2021-08-16 | 2021-10-04 | reflect on feedback 12/ | x
Observations of the Implementation of Cooperative Learning Structures | Leadership Team | All Teachers and Students | All teachers implement (2-3) cooperative learning structures. All students provide feedback via an age/grade appropriate reflection/ engagement exit ticket. Required observations: 2 with a lead teacher/coach and 1 peer observation. | 2021-10-04 |  | Cooperative Learning Planning Document Engagement Exit Tickets Engagement Visit Conversation Tool Engagement Visit Tool
Teachers reflect on feedback/observations and participate in regular discussions to improve practice. | Leadership Team | All Teachers and Students | All teachers will reflect and participate in discussion 3 times to identify an action step and improve their practice. | 2021-08-16 | 2021-12-13
PD on how to observe (with rubric) and deliver peer feedback before peer observation cycles begin | Leadership Team (maybe Kia too) |  |  | 2021-08-01 | 2021-10-17 | We reviewed the process and shared the rubric with staff during professional development in October and during our first round of engagement visit debriefs.
Teachers involve parents in cooperative learning structure team building activity at back to school night? or another parent night?
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #2 Spring 2021 | By the end of the year, all students will feel safe participating thoughtfully and intentionally in cooperative learning structures and restorative practices, understand the importance of engagement and value of restorative practices, and reflect on their engagement and restorative practices on a regular basis.
Milestone 3 | Students Engagement - Students understand the value of their engagement and are accountable for their engagement.
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Develop team reflections and/or engagement exit tickets for students to provide feedback to teachers on engagement and cooperative learning. | Leadership Team | All Students | Teachers elicit feedback via reflection or engagement exit ticket after implementing cooperative learning structures. | 11/1/2021 (shared exit tickets)
Develop a rubric for students to self-assess their engagment and to provide feedback to teachers. | Leadership Team | All Teachers and Students |  | 2022-01-11
Create "Buddy System" for Engagement Visits. Conduct two buddy visits for cooperative learning. | Leadership Team/All Teachers | All Teachers | Fill out observation form for each buddy visit. | 2022-01-11
Build reflection of student engagment into the professional growth circle - reflection should occur at least once every six weeks. | Leadership Team | All Teachers | Meetings occur with positive feedback. | 11/15/2021 (first)
In a pd session, use a cooperative learning structure to review the value of student engagement and to undertand the importance of cognitive, emotional, and behavioral engagement. Determine how to impart this to our students. Instruct students on the importance of their behavioral, emotional, and cognitive engagement two times. | All Teachers | All students | student engagement rubric; staff reflection and goal setting | 2022-01-11
Designate 1 all school meeting to teaching students about engagement. | Leadership Team | All Teachers and Students |  | 2022-01-11
Day 2 Professional Development with Kagan | Sam | All Teachers | All teachers participate in training | 2022-02-11
Share information about engagement with parents via the weekly news and SAC meeting. | Sam | All parents. | Weekly news and SAC meeting agenda. | 2022-01-15
Designate an all school portfolio/reflection time in the master schedule. | All Teachers | All Students | All students reflect once a week on engagement and learning.
CReate and post visual reminders of the importance of engagement and cooperative learning structures in classrooms and common spaces. | Leadership team. | All |  | 2022-01-11
Designate staff meeting time to looking at results of student survey to “action plan” around engagement
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 4 | Students Ownership of Restorative Practices- Students understand the value of restorative practices and participate in restorative circles and solutions to interpersonal conflict.
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Create and post visual reminders of restorative language/ restorative practices (for example - the 4 RJ questions) in classrooms and common spaces. | Leadership team. | All |  | 2022-01-11
Involve students in restorative practices to build social-emotional safety and behavioral engagement in support of cooperative learning. | All Teachers | All Students | Student restorative practices rubric. Coaching. Observations. | 2021-11-30
Professional Development on Tier 2 Restorative Practices to address uptick in social-emotional needs/interpersonal conflicts in support of cooperative learning. | Leadership Team. | All teachers | Teachers will attend professional development that aligns cooperative learning, classbuilding, and restorative practices. | 2021-11-29 | 2021-11-29 | We reviewed the process and shared the rubric with staff during professional development in October and during our first round of engagement visit debriefs.
Engage in two buddy visits to view restorative practices by EOY. | All Teachers | All teachers |  | 2022-03-07
In a pd session, use cooperative or restorative practices to determine how to instruct students on restorative practices. Instruct students on restorative practices at two times. Instruct students on the importance of their behavioral, emotional, and cognitive engagement. | All Teachers | All students | student restorative practices rubric; staff reflection and goal setting | 2022-03-07
Create access to a Peace Place - and support peer to peer restorative conversations. | All Teachers | All Students | Observations. Visual assessment of peace place and peer mediation. Student Rubric. | 2022-01-11
One Lead Team member (Lizzy) and the School Counselor or Principal attend a train the trainer training with Resotrative Solutions | 2 lead educators | All
Schedule and carry out three Restorative Practices Coaching Days with Restorative Solutions. One day is committed to finalizing our parent-student handbook. | Leadership Team. | All Teachers | Updated student handbook. Restorative Practices | TBD
Schedule and carry out a Restorative Practices Parent and Student Information Night | Sam | Parents |  | TBD 3/7??
Collaborate with School Counselor and outside partner to train students in restorative practices. Develop implementation plan by 2/1/2022 | Sam and Leadership Team | Students and teachers |  | 2022-01-11
Update Parent Student Handbook for the 2022 school year - include restorative practices in disciplinary practices | Sam and Leadership team | All |  | 2022-01-01
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #3 Fall 2022 | CCS staff will sustain a commitment to cooperative learning and restorative practices. All students participate in cooperative learning structures and restorative practices to sustain and share their learning and thinking at least 3 times a week. All students reflect on their engagement once a week and restorative practices once a month.
Milestone 5 | Engagement and Portfolio Reflections
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Continue weekly regular student reflection/portfolios.
Leadership deep dive into blooms taxonomy and "sustained inquiry"
PD focus on sustained inquiry
Develop list of sentence stems for students to use when reflecting on growth in academic subjects and on non-academic experiences.
Develop School-wide/grade level Portfolio Guidelines and Rubrics/checklists for self/peer assessment
Determine Plan for student sharing of portfolios (Portfolio Night, April Conferences, EOY)
Milestone 6 | Restorative Practices
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #3 Spring 2022 | All teachers will report high levels of engagement in professional learning. All teachers will reflect on professional learning on a regular basis as measured by regualar professional developement feedback.
Milestone 7
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 8
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 9
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #4 Summer/Fall 2022 | END GOAL
Milestone 9
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date

## Monday PD Schedule
| Rise Meetings | Date | Goings On to Consider | PD Topic (Mon. Staff Meetings) | PD Time (hours) | Objective(s) | Structures | PD Sequence | Resource
1 | 10/1 3:30:00(Sam) | 2021-09-27 | 7-8 ODE | Choices? NWEA Data Dig + Teambuilding for Staff |  | Deeper Learning Topics
2 | 10/6/2021 3:30 (Lizzy) | 2021-10-04 |  | KAGAN Cooperative Learning PD Diana (rounds) | 1 hour | Why Engagement and C.L. for students
3 |  | 2021-10-11 | Engagement Visits (1 C.L. Lead) | Implementation Hour + Coaching Info | 1 hour | Measuring Engagement + Portfolio hour
4 |  | 2021-10-18 | Engagement Visits (1 C.L. Lead) | Deep Dive NWEA - Fractions and Informational Text | 1 hour | SEL in a Coopeartive Classroom
5 |  | 2021-10-25 | conferences 10/28,29 (Angie Leads) | Reflect and Grow - Visit Reflection & name 1 C.L. Action Step | 1 hour | Class building + structure
6 | 11/1/2021 Diana | 2021-11-01 |  | KAGAN Cooperative Learning PD - Lizzy (rallies) | 1 hour | Team building + Structure
7 |  | 2021-11-08 | Engagement Visits (2 C.L. Leads) (Wed/Thurs) | Implementation Hour + Visit Info (w/2 teachers) + engagement exit tickets | 1 hour | Why Structures (math worksheet teacher a,b,c) and Why PIES for Engagement
8 |  | 2021-11-15 |  | Reflect and Grow - Student Feedback | 1 hour | Portfolio Focus
9 |  | 2021-11-22 |  | Thanksgiving break | 1 hour
10 |  | 2021-11-29 | *11.29 PD + Engagement Visits (2 C.L. Leads) | Kagan Cooperative Learning PD - Angie | 1 hour | Restorative Practice - Brainstorm a problem/conflict that really didn't go well that you would like to redo with Randy - Thematic - bring themes to Randy and get his input.... run scenarios
11 |  | 2021-12-06 |  | Full Day PD + implementation hour | 1 hour
12 |  | 2021-12-13 |  | Reflect and Grow - PD feedback and plan for new year | 1 hour
13 |  | 2022-01-03 | no staff meeting
14 | 1/10 (Angie class building, team building and maybe academic) | 2022-01-10 | Engagement PD | Overview of Engagement - How to teach it - how to measure it. plan ASM; portfolio reflection time in master schedule? | 1 hour
15 |  | 2022-01-14 | Staff PD day | Share plan for Spring 2022 and budget | 1 hour
16 |  | 2022-01-24 |  | Kagan Cooperative Learning PD + Buddy Visit System (2 CL buddy visits and 2 RP buddy visits) - go over how to use the tool - engagement visit document and 15 minute debrief | 1 hour
17 |  | 2022-01-31 | Buddy Engagement visit planning time | Implementation Hour - Kagan structure warmup/teach observation tool *Sam - 4:45 must haves: observation tool in hands - class for structure; structure idea and exit ticket | 1 hour
18 |  | 2022-02-07 |  | Reflect and Grow - w/ engagement rubric (student self assessment) * kagan structure warm up (Lizzy) - Angie & Diana lead reflect & Grow, focus on exit ticket reflection with Three Step Inverview and Circle with Eng.Visit Reflection (how did it feel to watch?) | 1 hour
|  | 2022-02-11 | 2/11 Full Day PD | Kagan Day Two - | 1 hour
19 |  | 2022-02-14 | no staff meeting - lesson planning on your own - buddy visits | Implementation Hour; Buddy Visits, Kaci from RISE coming 1-3, can we have showcase? | 1 hour
20 | 2021-02-25 | 2022-02-21 | Facilities (or BE) Staff Meeting on 2/22 | buddy visits, (2/22, 2/23, 2/24)
21 |  | 2022-02-28 |  | Reflect and Grow - w/ engagement rubric (Final reflect and grow of Kagan CL PD) | 1 hour
22 |  | 2022-03-07 | parent RJ night??? (Randy 3/7, 3/8, 3/9)kjh | Restorative Practice PD - introduce student rubric - student instruction/ASM - peace corner - coaching visit from Randy | 1 hour
23 |  | 2022-03-14 | conferences Mar.17,18 - BE Tryouts? | Reflect and Grow - on student engagement
24 |  | 2022-04-04 | CMAS training + BE | Restorative Practice PD (introduce appreciation/ apologies/ and request circles) | 1 hour
25 |  | 2022-04-11 | CMAS /BIG Event | Restorative Practice implementation hour for BE (Peace Place kits) | 1 hour
26 |  | 2022-04-18 | CMAS /BIG Event | Restorative Practice implementation for BE | 1 hour
27 |  | 2022-04-26 | Full Day PD (Tuesday) | Teambuilding for Staff; Reflect and grow - Big Event and Restorative Practices | 1 hour | End MOY - 24 additional hours
28 |  | 2022-05-02 |  | Restorative Practices PD for ODE and EOY | 1 hour | ADD TO MOY?
29 |  | 2022-05-09 | Buddy Visit | Restorative Practices Implementation EOY and ODE | 1 hour
30 |  | 2022-05-16 |  | Restorative Practices Reflect and Grow | 1 hour
31 |  | 2022-05-23
32
33
34
35
36
37 |  |  | last day with staff
30- 1 hr. extra PD
Total |  |  |  |  | 10 coaching days (subs)

## PM1 (hidden)
School Name: | High Point Academy
Goal(s): | Teachers facilitate and maintain culturally responsive practices, expectations, and common language, within a strong classroom culture, that supports dependent and independent learners to engage in meaningful learning experiences and progress toward proficiency of learning goals.
CfS Related Strategy 1
Increase staff members understanding and ownership of their identity, biases, microaggressions, triggers and how policies, procedures, systems, structures and interactions impact how they contribute to the experiences of all students.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Quarterly Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide explicit professional development on identity, bias, culture, microagrressions, and culturally responsive teaching practices throughout trimester 2 | Teachers | BLT | CfS funded | Created and implemented PD plans | 2021-02-26 |  |  |  |  | x | x | x |  | x |  |  | x | x
Facilitate biweekly 30-40 minute staff gatherings focused on chapters and topics from Culturally Responsive Teaching and the Brain with a resulting schoolwide action step | Teachers | BLT | CfS funded | Weekly gathering plans | 2021-02-26
Collect feedback and reflection data about staff reflections and reactions | Teachers | Admin team and BLT | CfS funded | Feedback data organized and analyzed for conclusions | 2021-02-26 |  |  |  |  | x | x | x |  | x |  |  | x | x
Create a system to track staff reflections and progress about their own awareness | BLT | Admin team | CfS funded | Data tracker with at least one completed column for trimester 2 | 2021-01-30 |  |  |  |  | x | x | x |  | x |  |  |  | x |  |  |  | x
Staff members are regularly presenting and reflecting on identity boards to build increased awareness of our socialization and racialized worl view. | Teachers | Admin team and BLT | No resources | Identity board sessions scheduled in PD calendar | 2021-02-26 |  |  | x | [5 empty] | x
CfS Related Strategy 2
Utilize frequent formative assessment data to provide, monitor, and adjust instruction both proactively and in-the-moment, so that students receive targeted, culturally responsive instruction during tier one learning blocks to meet their needs.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide "Lead Learner" professional development to BLT members during bi-weekly professional development. | BLT | Admin team | CfS funded | Professional development plans created and implemented | 2021-02-26 |  |  | x | x |  | x | x | [5 empty] | x | x
Provide professional development on culturally resposive tier-1 lesson planning to all staff | Teachers | BLT and Admin team | CfS funded | Professional development plans created and implemented | 2021-01-15 |  |  | x | x | x | x | x | x |  | x | x | x | x | x
Provide staff members with feedback on tier-1 lesson plans | Teachers | Admin team | No resources | Lesson plans with feedback recorded on the tracker | 2021-02-26 |  |  | x | x |  | x | x | x |  | x |  |  | x | x
Create a protocol that BLT members will use to facilitate data team meetings so that plans are responsive to student needs and tier one instruction improves. | BLT and teachers | Admin team | CfS funded | Protocol created | 2021-02-01 |  |  | x | x |  | x | x | x |  | x |  |  | x | x | x
Create a "Culture Code 2.0" walkthrough tool that measures the implementation of culturally responsive teaching. | Teachers | BLT | CfS funded | Tool and tracker created | 2021-02-01 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
Share the Culture Code 2.0 with staff for feedback and to develop understanding | Teachers | BLT | CfS funded | Revised tool | 2021-02-26 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
Create and implement a "Culture Code 2.0" walkthrough plan | Teachers | BLT | CfS funded | At least 1 walktrhough per teacher is created and the data is entered | 2021-02-26 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
CfS Related Strategy 3
Build meaningful relationships and authentic partnerships with families that foster mutual trust, understanding, and appreciation across cultures and other differences in order to develop and advance a shared definition of student success.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Schedule and implement regular "Coffee with Keri" events | HPA Families | Admin team | No resources | Coffee with Keri events are scheduled and publicized | 2021-02-26 |  | x | [6 empty] | x
Include parent input and voice with the charter renewal process | HPA Families | Admin team | No resources | Charter renewal documents | 2021-02-26 |  | x | [6 empty] | x
Survey families about learning structure needs | HPA Families | Admin team | No resources | Organized survey data | 2021-02-26 |  | x | [6 empty] | x
Provide funding for childcare and computers | HPA Families | Admin team | No resources | Funding documentation | 2021-02-26 |  | x | [6 empty] | x
Create a Family Council Plan and Structure with the charter board | HPA Families | Admin team | No resources | Family Council Plan | 2021-02-26 |  | x | [6 empty] | x |  |  | x |  |  |  |  | x
CfS Related Strategy 4
Increase staff buy-in and skills through explicit and targeted school-wide professional development.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide professional development models and PD planning time to members of the Building Leadership Team (BLT) during December BLT meetings to prepare for January and February PD | BLT | Admin team | CfS funded | Planned and implemented retreat BLT plans | 2021-12-20 |  |  |  | x | x | x | x | [8 empty] | x | [5 empty] | x | x | x
Create professional development plans for the Jan and Feb PD with BLT. | Teachers | BLT and Admin team | No resources | Planned and implemented PD plans | 2021-12-20 |  |  |  |  | x | x | x | [8 empty] | x | [5 empty] | x | x | x
Plan and implement Jan Professional Development focused on recognizing and providing friction for bias in the classroom | Teachers | Principal and Dean | No resources | Planned and implemented PD plans | 2020-01-30 |  |  |  |  | x | x | x | [5 empty] | x |  |  | x | x |  |  |  |  | x | x | x
Plan and implement Feb Professional Development focused on recognizing and providing friction for bias in the classroom | Teachers | BLT and Admin team | CfS funded | Planned and implemented October 17th PD plans | 2020-02-26 |  |  |  |  | x | x | x | [5 empty] | x |  |  | x | x |  |  |  |  | x | x | x
Admin book study on Student-Centered Coaching (APs + BLT members) | Assistant Principals and BLT members | Executive Director | No resources | Book study agenda and artifacts | 2020-02-26 | [5 empty] | x |  |  |  | x |  |  |  | x | x
Admin book study on Courageous Conversations | Deans | Executive Director | No resources | Book study agenda and artifacts | 2020-02-26 | [5 empty] | x |  |  |  | x |  |  |  | x | x
CfS Related Strategy 5
Build a system of distributed leadership to increase capacity and build buy-in by establishing a Building Leadership Team.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide "lead learner" professional development about equity, bias, and culturally responsive practices during bi-weekly BLT meetings | BLT | Admin team | CfS funded | Planned and implemented BLT agenda and work products | 2021-02-26 |  |  |  | x | [11 empty] | x | [5 empty] | x |  | x
Facilitate weekly staff gatherings focused on chapters and topics from Culturally Responsive Teaching and the Brain | Teachers | BLT | CfS funded | Planned and implemented gathering agendas | 2021-02-26
Co-facilitate Professional Development during January and February PD sessions | Teachers | BLT | No resources | Planned and implemented agendas | 2021-02-26 |  |  |  | x | x | [16 empty] | x | x | x
Monthly logistics meetings | BLT | Admin team | No resources | Evidence that meeting agendas have been planned and implemented | 2021-02-26 |  |  |  | x | [12 empty] | x
Bi-weekly mentor check-ins | BLT | Admin team | No resources | Each BLT member has had at least 5 check-ins with their mentor | 2021-02-26 |  |  |  | x |  | x | [9 empty] | x | x
CfS Related Strategy 6
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 7
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 8
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 9
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 10
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments