## Implementation Plan
Engagement Strategy | By implementing the Universal Design for Learning framework, teachers will increase students' cognitive and emotional engagement and thereby more fully live out our mission of developing young people who are the agents of their own education.
Engagement Need Alignment | On the Mental Model Survey, MacLaren students' cognitive engagement and emotional engagement tended to be lower than we had hoped to see. While this was not always aligned to the results of the Engagement Assessment Tool piloted in classrooms, we saw an opportunity to grow as a school and better fulfill our mission and vision.
Root Causes Alignment | The root causes of the engagement need are not entirely clear. Our IEP and ELL caseload have increased 150% and 135% respectively since we moved to our new location in 2017-18, and we know that our teachers need training to better serve this more diverse population. That said, it is also possible that some of the discrepancies between the MMS and the EAT are due simply to the way the questions were framed (such that students may have been led to report engagement negatively due to neutral or even positive factors like uniforms or academic culture).
Implementation Goal | The goal of UDL implementation is to increase students' engagement on multiple measures: 1) Cognitive and emotional engagement will increase on the revised Mental Model Survey, to be administed in August 2021. 2) Results from the Engagement Assessment Tool will align to the Mental Model Survey. 3) On the Upper School student survey, students will report decreased anxiety.
Baseline Data Points Spring 2021 | (input baseline data point)
Interim Target #1 Fall 2021 | (set target #1)
Milestone 1
By the end of Q1, all MacLaren teachers will be able to articulate curricularly-aligned Learning Goals for each lesson, and will be able to distinguish them from activities.
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Professional Development | Hall/Alvarado | Faculty | All faculty trained in UDL | 2021-08-05 | 2021-08-05 | Training materials from summer training
Classroom Observations | Team Leads & RISE team | Faculty | Learning Goals clearly written and articulated in each classroom | 2021-08-10 | 2021-10-11 | Classroom observation tool
Team meetings | Team Leads & RISE team | Faculty | Meetings have been scheduled for this quarter to evaluate effectiveness of use of Learning Goal and to determine next steps
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 2
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 3
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #2 Winter 2021 | (set target #2)
Milestone 4
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 5
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 6
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #3 Spring 2022 | (set target #3)
Milestone 7
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 8
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 9
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #4 Summer/Fall 2022 | END GOAL
Milestone 9
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date

## Example
Engagement Strategy | Teachers will increase the students' cognitive lift and cognitive engagement through strategically planning questions using Bloom's and scripting the right answer they are looking for in students' responses.
Engagement Need Alignment | Observations yielded that students are not doing the cognitive lift in the classroom. In 5 classrooms, observers marked that teachers were doing 75-100% of the cognitive lift. In 4/5 classrooms, teachers did not move past "Understanding" question levels on Bloom's taxonomy.
Root Causes Alignment | Teachers lack strong questioning skills. By implementing building their skills and then implementing this strategy teachers will be required to be strategic and intentional with their planning of questioning.
Implementation Goal | In 4/5 classrooms, teacher talk will shift to 50 percent of the cognitive lift or below as evidenced by walkthroughs. In 4/5 classrooms, teachers will move between "remember/undersand" and "apply" and above as evidenced by walkshroughs and tasks students are completing.
Baseline Data Points Spring 2021 | In 5 classrooms, observers marked that teachers were doing 75-100% of the cognitive lift. In 4/5 classrooms, teachers did not move past "Understanding" question levels on Bloom's taxonomy.
Interim Target #1 Fall 2021 | (set target #1)
Milestone 1
By June 30th, 2021, cohort team members will set a Vision for this strategy implementation.
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
clearly articulate the "why" behind this shift in planning expectations | Kaci | Cohort team members | documented in slide deck | June 16th | June 20th
clearly articulate new planning expectations | Kaci | Cohort team members | documented in slide deck | June 16th | June 20th
define coaching expectations and look fors | Morgan | Cohort team members | Look For document | June 20th | June 25th
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 2
Develop a professional development scope and sequence aligned to the articulated vision.
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Consider our staff skills and needs
determine timeline for pd and training
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 3
Action Steps | Personnel on Point | Targeted Stakeholders | Measurable Implementation Benchmark/Success Critera | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges and Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #2 Winter 2021 | (set target #2)
Milestone 4
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 5
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 6
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #3 Spring 2022 | (set target #3)
Milestone 7
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 8
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Milestone 9
By (date)...(what will be happening)
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
Interim Target #4 Summer/Fall 2022 | END GOAL
Milestone 9
Action Steps | Personnel on Point | Key Stakeholders | Measurable Implementation Benchmark | Timeline |  | Linked Documents and Products | Check and Act
|  |  |  | Start | End |  | Completed | Challenges | Comments
Monitoring and Adjustment
Date | Date | Date | Date | Date | Date | Date | Date | Date | Date

## PM1 (hidden)
School Name: | High Point Academy
Goal(s): | Teachers facilitate and maintain culturally responsive practices, expectations, and common language, within a strong classroom culture, that supports dependent and independent learners to engage in meaningful learning experiences and progress toward proficiency of learning goals.
CfS Related Strategy 1
Increase staff members understanding and ownership of their identity, biases, microaggressions, triggers and how policies, procedures, systems, structures and interactions impact how they contribute to the experiences of all students.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Quarterly Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide explicit professional development on identity, bias, culture, microagrressions, and culturally responsive teaching practices throughout trimester 2 | Teachers | BLT | CfS funded | Created and implemented PD plans | 2021-02-26 |  |  |  |  | x | x | x |  | x |  |  | x | x
Facilitate biweekly 30-40 minute staff gatherings focused on chapters and topics from Culturally Responsive Teaching and the Brain with a resulting schoolwide action step | Teachers | BLT | CfS funded | Weekly gathering plans | 2021-02-26
Collect feedback and reflection data about staff reflections and reactions | Teachers | Admin team and BLT | CfS funded | Feedback data organized and analyzed for conclusions | 2021-02-26 |  |  |  |  | x | x | x |  | x |  |  | x | x
Create a system to track staff reflections and progress about their own awareness | BLT | Admin team | CfS funded | Data tracker with at least one completed column for trimester 2 | 2021-01-30 |  |  |  |  | x | x | x |  | x |  |  |  | x |  |  |  | x
Staff members are regularly presenting and reflecting on identity boards to build increased awareness of our socialization and racialized worl view. | Teachers | Admin team and BLT | No resources | Identity board sessions scheduled in PD calendar | 2021-02-26 |  |  | x | [5 empty] | x
CfS Related Strategy 2
Utilize frequent formative assessment data to provide, monitor, and adjust instruction both proactively and in-the-moment, so that students receive targeted, culturally responsive instruction during tier one learning blocks to meet their needs.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide "Lead Learner" professional development to BLT members during bi-weekly professional development. | BLT | Admin team | CfS funded | Professional development plans created and implemented | 2021-02-26 |  |  | x | x |  | x | x | [5 empty] | x | x
Provide professional development on culturally resposive tier-1 lesson planning to all staff | Teachers | BLT and Admin team | CfS funded | Professional development plans created and implemented | 2021-01-15 |  |  | x | x | x | x | x | x |  | x | x | x | x | x
Provide staff members with feedback on tier-1 lesson plans | Teachers | Admin team | No resources | Lesson plans with feedback recorded on the tracker | 2021-02-26 |  |  | x | x |  | x | x | x |  | x |  |  | x | x
Create a protocol that BLT members will use to facilitate data team meetings so that plans are responsive to student needs and tier one instruction improves. | BLT and teachers | Admin team | CfS funded | Protocol created | 2021-02-01 |  |  | x | x |  | x | x | x |  | x |  |  | x | x | x
Create a "Culture Code 2.0" walkthrough tool that measures the implementation of culturally responsive teaching. | Teachers | BLT | CfS funded | Tool and tracker created | 2021-02-01 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
Share the Culture Code 2.0 with staff for feedback and to develop understanding | Teachers | BLT | CfS funded | Revised tool | 2021-02-26 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
Create and implement a "Culture Code 2.0" walkthrough plan | Teachers | BLT | CfS funded | At least 1 walktrhough per teacher is created and the data is entered | 2021-02-26 |  |  | x | x | x | x | x |  |  |  | x | x | x | x | x |  | x
CfS Related Strategy 3
Build meaningful relationships and authentic partnerships with families that foster mutual trust, understanding, and appreciation across cultures and other differences in order to develop and advance a shared definition of student success.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Schedule and implement regular "Coffee with Keri" events | HPA Families | Admin team | No resources | Coffee with Keri events are scheduled and publicized | 2021-02-26 |  | x | [6 empty] | x
Include parent input and voice with the charter renewal process | HPA Families | Admin team | No resources | Charter renewal documents | 2021-02-26 |  | x | [6 empty] | x
Survey families about learning structure needs | HPA Families | Admin team | No resources | Organized survey data | 2021-02-26 |  | x | [6 empty] | x
Provide funding for childcare and computers | HPA Families | Admin team | No resources | Funding documentation | 2021-02-26 |  | x | [6 empty] | x
Create a Family Council Plan and Structure with the charter board | HPA Families | Admin team | No resources | Family Council Plan | 2021-02-26 |  | x | [6 empty] | x |  |  | x |  |  |  |  | x
CfS Related Strategy 4
Increase staff buy-in and skills through explicit and targeted school-wide professional development.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide professional development models and PD planning time to members of the Building Leadership Team (BLT) during December BLT meetings to prepare for January and February PD | BLT | Admin team | CfS funded | Planned and implemented retreat BLT plans | 2021-12-20 |  |  |  | x | x | x | x | [8 empty] | x | [5 empty] | x | x | x
Create professional development plans for the Jan and Feb PD with BLT. | Teachers | BLT and Admin team | No resources | Planned and implemented PD plans | 2021-12-20 |  |  |  |  | x | x | x | [8 empty] | x | [5 empty] | x | x | x
Plan and implement Jan Professional Development focused on recognizing and providing friction for bias in the classroom | Teachers | Principal and Dean | No resources | Planned and implemented PD plans | 2020-01-30 |  |  |  |  | x | x | x | [5 empty] | x |  |  | x | x |  |  |  |  | x | x | x
Plan and implement Feb Professional Development focused on recognizing and providing friction for bias in the classroom | Teachers | BLT and Admin team | CfS funded | Planned and implemented October 17th PD plans | 2020-02-26 |  |  |  |  | x | x | x | [5 empty] | x |  |  | x | x |  |  |  |  | x | x | x
Admin book study on Student-Centered Coaching (APs + BLT members) | Assistant Principals and BLT members | Executive Director | No resources | Book study agenda and artifacts | 2020-02-26 | [5 empty] | x |  |  |  | x |  |  |  | x | x
Admin book study on Courageous Conversations | Deans | Executive Director | No resources | Book study agenda and artifacts | 2020-02-26 | [5 empty] | x |  |  |  | x |  |  |  | x | x
CfS Related Strategy 5
Build a system of distributed leadership to increase capacity and build buy-in by establishing a Building Leadership Team.
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Provide "lead learner" professional development about equity, bias, and culturally responsive practices during bi-weekly BLT meetings | BLT | Admin team | CfS funded | Planned and implemented BLT agenda and work products | 2021-02-26 |  |  |  | x | [11 empty] | x | [5 empty] | x |  | x
Facilitate weekly staff gatherings focused on chapters and topics from Culturally Responsive Teaching and the Brain | Teachers | BLT | CfS funded | Planned and implemented gathering agendas | 2021-02-26
Co-facilitate Professional Development during January and February PD sessions | Teachers | BLT | No resources | Planned and implemented agendas | 2021-02-26 |  |  |  | x | x | [16 empty] | x | x | x
Monthly logistics meetings | BLT | Admin team | No resources | Evidence that meeting agendas have been planned and implemented | 2021-02-26 |  |  |  | x | [12 empty] | x
Bi-weekly mentor check-ins | BLT | Admin team | No resources | Each BLT member has had at least 5 check-ins with their mentor | 2021-02-26 |  |  |  | x |  | x | [9 empty] | x | x
CfS Related Strategy 6
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 7
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 8
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 9
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
CfS Related Strategy 10
Action Steps | Intended Recipient(s) | Intended Provider(s) | Funding Used (dropdown) | Measurable Implementation Milestone | Timeline |  | Report Recommendations Addressed | [6 empty] | HAS Findings Addressed | [8 empty] | Evaluation
[5 empty] | Target Date | Completion Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Relationships | Time | Monitoring | Decisions | Expectations | Learning | Language | Resources | Cont. Imp. | Met Target | Challenges | Implemented with Fidelity | Comments
Note on I9: ====== ID#AAAAH2mWWPo Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J9: ====== ID#AAAAH2mWWTg Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K9: ====== ID#AAAAH2mWWT8 Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L9: ====== ID#AAAAH2mWWTk Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M9: ====== ID#AAAAH2mWWUg Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N9: ====== ID#AAAAH2mWWPw Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O9: ====== ID#AAAAH2mWWQQ Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P9: ====== ID#AAAAH2mWWRI Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q9: ====== ID#AAAAH2mWWM0 Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R9: ====== ID#AAAAH2mWWR4 Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S9: ====== ID#AAAAH2mWWPM Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T9: ====== ID#AAAAH2mWWO0 Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U9: ====== ID#AAAAH2mWWL0 Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V9: ====== ID#AAAAH2mWWNY Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W9: ====== ID#AAAAH2mWWMA Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X9: ====== ID#AAAAH2mWWK8 Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I24: ====== ID#AAAAH2mWWRo Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J24: ====== ID#AAAAH2mWWPs Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K24: ====== ID#AAAAH2mWWOk Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L24: ====== ID#AAAAH2mWWSk Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M24: ====== ID#AAAAH2mWWLQ Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N24: ====== ID#AAAAH2mWWUQ Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O24: ====== ID#AAAAH2mWWPQ Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P24: ====== ID#AAAAH2mWWME Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q24: ====== ID#AAAAH2mWWTM Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R24: ====== ID#AAAAH2mWWUY Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S24: ====== ID#AAAAH2mWWSo Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T24: ====== ID#AAAAH2mWWQg Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U24: ====== ID#AAAAH2mWWRk Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V24: ====== ID#AAAAH2mWWS0 Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W24: ====== ID#AAAAH2mWWPc Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X24: ====== ID#AAAAH2mWWOg Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I36: ====== ID#AAAAH2mWWOo Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J36: ====== ID#AAAAH2mWWOQ Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K36: ====== ID#AAAAH2mWWRc Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L36: ====== ID#AAAAH2mWWN0 Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M36: ====== ID#AAAAH2mWWLg Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N36: ====== ID#AAAAH2mWWNM Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O36: ====== ID#AAAAH2mWWLU Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P36: ====== ID#AAAAH2mWWMY Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q36: ====== ID#AAAAH2mWWT0 Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R36: ====== ID#AAAAH2mWWNg Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S36: ====== ID#AAAAH2mWWLs Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T36: ====== ID#AAAAH2mWWTY Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U36: ====== ID#AAAAH2mWWM8 Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V36: ====== ID#AAAAH2mWWP8 Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W36: ====== ID#AAAAH2mWWUk Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X36: ====== ID#AAAAH2mWWSI Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I47: ====== ID#AAAAH2mWWLA Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J47: ====== ID#AAAAH2mWWPE Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K47: ====== ID#AAAAH2mWWQ8 Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L47: ====== ID#AAAAH2mWWSc Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M47: ====== ID#AAAAH2mWWUU Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N47: ====== ID#AAAAH2mWWP4 Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O47: ====== ID#AAAAH2mWWNA Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P47: ====== ID#AAAAH2mWWTw Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q47: ====== ID#AAAAH2mWWQI Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R47: ====== ID#AAAAH2mWWL4 Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S47: ====== ID#AAAAH2mWWSA Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T47: ====== ID#AAAAH2mWWMI Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U47: ====== ID#AAAAH2mWWMo Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V47: ====== ID#AAAAH2mWWMw Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W47: ====== ID#AAAAH2mWWRY Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X47: ====== ID#AAAAH2mWWRw Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I61: ====== ID#AAAAH2mWWPU Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J61: ====== ID#AAAAH2mWWRs Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K61: ====== ID#AAAAH2mWWQA Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L61: ====== ID#AAAAH2mWWRQ Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M61: ====== ID#AAAAH2mWWM4 Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N61: ====== ID#AAAAH2mWWSs Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O61: ====== ID#AAAAH2mWWQ0 Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P61: ====== ID#AAAAH2mWWTo Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q61: ====== ID#AAAAH2mWWTQ Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R61: ====== ID#AAAAH2mWWMM Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S61: ====== ID#AAAAH2mWWPg Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T61: ====== ID#AAAAH2mWWNk Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U61: ====== ID#AAAAH2mWWSw Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V61: ====== ID#AAAAH2mWWRM Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W61: ====== ID#AAAAH2mWWO8 Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X61: ====== ID#AAAAH2mWWL8 Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I73: ====== ID#AAAAH2mWWOM Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J73: ====== ID#AAAAH2mWWTs Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K73: ====== ID#AAAAH2mWWUM Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L73: ====== ID#AAAAH2mWWMU Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M73: ====== ID#AAAAH2mWWQE Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N73: ====== ID#AAAAH2mWWRg Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O73: ====== ID#AAAAH2mWWLw Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P73: ====== ID#AAAAH2mWWN4 Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q73: ====== ID#AAAAH2mWWMc Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R73: ====== ID#AAAAH2mWWS4 Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S73: ====== ID#AAAAH2mWWN8 Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T73: ====== ID#AAAAH2mWWUE Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U73: ====== ID#AAAAH2mWWPI Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V73: ====== ID#AAAAH2mWWQo Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W73: ====== ID#AAAAH2mWWMQ Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X73: ====== ID#AAAAH2mWWPk Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I88: ====== ID#AAAAH2mWWO4 Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J88: ====== ID#AAAAH2mWWS8 Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K88: ====== ID#AAAAH2mWWUs Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L88: ====== ID#AAAAH2mWWLc Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M88: ====== ID#AAAAH2mWWPY Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N88: ====== ID#AAAAH2mWWSY Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O88: ====== ID#AAAAH2mWWLY Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P88: ====== ID#AAAAH2mWWQc Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q88: ====== ID#AAAAH2mWWOA Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R88: ====== ID#AAAAH2mWWLo Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S88: ====== ID#AAAAH2mWWUw Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T88: ====== ID#AAAAH2mWWMg Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U88: ====== ID#AAAAH2mWWR0 Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V88: ====== ID#AAAAH2mWWRE Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W88: ====== ID#AAAAH2mWWU0 Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X88: ====== ID#AAAAH2mWWNw Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I103: ====== ID#AAAAH2mWWQU Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J103: ====== ID#AAAAH2mWWPA Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K103: ====== ID#AAAAH2mWWUI Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L103: ====== ID#AAAAH2mWWQk Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M103: ====== ID#AAAAH2mWWQY Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N103: ====== ID#AAAAH2mWWT4 Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O103: ====== ID#AAAAH2mWWQs Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P103: ====== ID#AAAAH2mWWQ4 Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q103: ====== ID#AAAAH2mWWNE Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R103: ====== ID#AAAAH2mWWOU Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S103: ====== ID#AAAAH2mWWQM Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T103: ====== ID#AAAAH2mWWOs Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U103: ====== ID#AAAAH2mWWLE Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V103: ====== ID#AAAAH2mWWMs Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W103: ====== ID#AAAAH2mWWQw Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X103: ====== ID#AAAAH2mWWSU Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I118: ====== ID#AAAAH2mWWNc Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J118: ====== ID#AAAAH2mWWTc Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K118: ====== ID#AAAAH2mWWRU Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L118: ====== ID#AAAAH2mWWOY Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M118: ====== ID#AAAAH2mWWLM Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N118: ====== ID#AAAAH2mWWSM Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O118: ====== ID#AAAAH2mWWNo Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P118: ====== ID#AAAAH2mWWRA Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q118: ====== ID#AAAAH2mWWOE Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R118: ====== ID#AAAAH2mWWTI Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S118: ====== ID#AAAAH2mWWLk Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T118: ====== ID#AAAAH2mWWNQ Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U118: ====== ID#AAAAH2mWWSg Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V118: ====== ID#AAAAH2mWWUc Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W118: ====== ID#AAAAH2mWWOw Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X118: ====== ID#AAAAH2mWWOc Negley, Tina (2021-02-18 00:29:40) Continuous improvement
Note on I133: ====== ID#AAAAH2mWWSE Negley, Tina (2021-02-18 00:29:40) Explore ways to actively engage a more diverse parent group and interact with members of various cultures.
Note on J133: ====== ID#AAAAH2mWWUo Negley, Tina (2021-02-18 00:29:40) Evaluate and focus initiatives to ensure alignment with school goals and priorities. Ensure sufficient time is provided for implementing initiatives with fidelity.
Note on K133: ====== ID#AAAAH2mWWOI Negley, Tina (2021-02-18 00:29:40) Distribute decision-making when possible and clearly communicate, to all stakeholders, decisions made and how they best support students.
Note on L133: ====== ID#AAAAH2mWWUA Negley, Tina (2021-02-18 00:29:40) Implement classroom and behavior management with consistency and constancy across the school. Provide training, monitoring, and feedback to ensure that consistent behavior practices are implemented schoolwide.
Note on M133: ====== ID#AAAAH2mWWTU Negley, Tina (2021-02-18 00:29:40) Provide training, support, follow-up coaching, and structures to improve high-leverage instructional practices and differentiated instruction, and ensure that common language is being consistently used schoolwide.
Note on N133: ====== ID#AAAAH2mWWR8 Negley, Tina (2021-02-18 00:29:40) Ensure that all staff establish and uphold high academic and behavioral expectations for each and every student.
Note on O133: ====== ID#AAAAH2mWWLI Negley, Tina (2021-02-18 00:29:40) Create structures, protocols, and time for co-planning and collaboration across grades, content, and teams, including ELD and SPED specialists. Provide training and support around using data for planning and to inform instruction.
Note on P133: ====== ID#AAAAH2mWWP0 Negley, Tina (2021-02-18 00:29:40) Relationships are valued
Note on Q133: ====== ID#AAAAH2mWWK4 Negley, Tina (2021-02-18 00:29:40) Time is invested and protected
Note on R133: ====== ID#AAAAH2mWWSQ Negley, Tina (2021-02-18 00:29:40) Performance monitoring is purposeful, frequent, and effectively used
Note on S133: ====== ID#AAAAH2mWWNU Negley, Tina (2021-02-18 00:29:40) Decisions are student-centered
Note on T133: ====== ID#AAAAH2mWWMk Negley, Tina (2021-02-18 00:29:40) Expectations are set high, made explicit, frequently expressed, and consistently applied
Note on U133: ====== ID#AAAAH2mWWTE Negley, Tina (2021-02-18 00:29:40) Learning is purposefully and meaningfully structured
Note on V133: ====== ID#AAAAH2mWWTA Negley, Tina (2021-02-18 00:29:40) Staff intentionally uses common language for consistent messaging
Note on W133: ====== ID#AAAAH2mWWNI Negley, Tina (2021-02-18 00:29:40) Capitalizing on available resources
Note on X133: ====== ID#AAAAH2mWWNs Negley, Tina (2021-02-18 00:29:40) Continuous improvement